## Sheet1
No | Task | Actor | Date | Time Spent
1 | Setup Github accounts and master | Peter, Cesar, Conor , Kingsley | 2012-06-03 | 2 hours
2 | Wireframes V1.0 | Peter, Cesar, Conor | 2012-06-06 | 5 hours
3 | Github Wiki | Peter | 2012-06-12 | 2 hours
4 | Project Proposal | Conor |  | 2 hours
5 | Conversion of Music Store Catalog to Car Auctions | Cezar | 2012-07-04 | 15 hours
6 | Auction Use Cases | Cezar | 2012-07-11 | 1 hour
7 | Project Status Meeting - Peter and Kingsley Removed | Adrian Skehill | 2012-07-14 | 20 min
8 | Bidding Functionality | Cezar, Conor | 2012-07-16 | 16 hours
7 | Login/Logout Functionality | Conor | 2012-07-17 | 4 hours
8 | Bidding Functionality | Cezar, Conor | 2012-07-18 | 16 hours
9 | DAL Layer | Conor | 19-20/07/2012 | 12 hours
10 | Images and CSS rules | Cezar | 19-20/07/2012 | 3 hours
11 | DAL Layer | Conor | 22-23/07/2012 | 10 hours
12 | BLL Layer | Conor | 2012-07-23 | 3 hours
13 | EF Scaling to SQL Server | Cezar | 22-23/07/2012 | 8 hours
14 | EF Scaling to SQL Server | Conor | 23-24/07/2012 | 8 hours
15 | Bidding Functionality | Cezar | 2012-07-24 | 6 hours
16 | Unit Testing | Conor | 2012-07-24 | 1 hour
17 | Completed Bidding Functionality | Cezar, Conor | 2012-07-24 | 2 hours
18 | EF Scaling to SQL Server | Cezar | 2012-07-25 | 8 hours
19 | Unit Testing | Conor | 2012-07-25 | 6 hours
20 | EF Scaling to SQL Server | Cezar | 2012-07-26 | 8 hours
21 | Documentation | Conor | 2012-07-26 | 8 hours
22 | EF Scaling to SQL Server | Cezar | 2012-07-27 | 2 hours
22 | Unit Testing | Cezar | 2012-07-27 | 2 hours
23 | Documentation | Conor | 2012-07-27 | 4 hours
24 | Bidding History | Cezar, Conor | 2012-07-27 | 8 hours
24 | Documentation Review and Update | Cezar, Conor | 2012-07-28 | 4 hours
25 | Upload of Deliverables to Final Demo Github Repository | Cezar, Conor | 2012-07-28 | 2 hours